## 17-239
Task Name | Estimate time( hour) | Take by | Actual Time | Status | Date Doing | Complete Process | Note
Requirement analyze | 5 | Truong Van Khoi |  | Done |  | 0
[Report 1] Project Information | 2 | Nguyen Bao Thien |  | Done |  | 2
[Report 1] Introduction | 2 | Nguyen Bao Thien |  | Done |  | 2
[Report 1] Current Situation | 2 | Nguyen Bao Thien |  | Done |  | 2
[Report 1] Problem Definition | 2 | Nguyen Bao Thien |  | Done |  | 2
Database analyze | 10 | Nguyen Bao Thien |  | Done |  | 10
Total | 23 |  | 46.94% |  | Done task: | 78.26%
[UI Mockup Web] User's Tour Detail Screen | 9 | Nguyen Bao Thien |  | Done |  | 9
[UI Mockup Web] User's Tour Detail | 15 | Nguyen Bao Thien |  | Done |  | 12
[UI Mockup Web] User's Login/Regrister/Logout Screen | 3 | Nguyen Bao Thien |  | Done |  | 2
[UI Mockup Web] User's Login/Regrister/Logout | 3 | Nguyen Bao Thien |  | Done |  | 2
[UI Mockup Web] User's Booking history | 2 | Nguyen Bao Thien |  | Done |  | 2
[UI Mockup Web] User's Booking history screen | 2 | Nguyen Bao Thien |  | Done |  | 2
[UI Mockup Web] User's Booking | 10 | Nguyen Bao Thien |  | Done |  | 8
[UI Mockup Web] User's Booking Screen | 3 | Nguyen Bao Thien |  | Done |  | 2
Learning ASP.NET MVC Performance | 10 | Nguyen Bao Thien |  | None |  | 10
Learning ASP.NET MVC Security | 10 | Nguyen Bao Thien |  | None |  | 10
Total | 67 |  | 136.7% |  | Done task: | 88.06%
Learning ASP.NET Core v2.1 | 16 | Nguyen Nghia Mai Linh |  | Done |  | 18
Learning Entity Framework | 3 | Nguyen Nghia Mai Linh |  | Done |  | 3
[UI Mockup Web] Admin Login/Register Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin Home Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's User Management Screen | 8 | Nguyen Nghia Mai Linh |  | Done |  | 4
[UI Mockup Web] Admin's Passenger Management Screen | 3 | Nguyen Nghia Mai Linh |  | Done |  | 3
[UI Mockup Web] Admin's Travel Type Management Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Booking Management Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Tour Management Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Region Management Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Image management screen | 1 | Nguyen Nghia Mai Linh |  | Fail
[UI Mockup Web] Admin's Hotel management screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's City management screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Office management screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Country Management Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Tour Guide management screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Booking Management Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Report Screen | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Create entity model | 3 | Nguyen Nghia Mai Linh |  | Done |  | 4
[UI Mockup Web] Admin's Tour Controller | 4 | Nguyen Nghia Mai Linh |  | Done |  | 5
[UI Mockup Web] Admin's Tour Detail Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Admin Controller | 8 | Nguyen Nghia Mai Linh |  | Done |  | 7
[UI Mockup Web] Admin's User Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Travel Type Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Tour Guide Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Image Controller | 1 | Nguyen Nghia Mai Linh |  | Fail |  | 0
[UI Mockup Web] Admin's Passenger Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Country Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Hotel Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Home Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Booking Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's City Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
[UI Mockup Web] Admin's Tour Detail Controller | 1 | Nguyen Nghia Mai Linh |  | Done |  | 1
Total | 52 |  | 106.1% |  | Done task: | 90.38%
Learning ASP .NET MVC5 | 14 | Truong Van Khoi |  | Done |  | 8
Learning Entity Framework | 2 | Truong Van Khoi |  | Done |  | 2
[UI Mockup Web] User's Home Screen | 3 | Truong Van Khoi |  | Done |  | 3
[UI Mockup Web] User's Travel Screen | 2 | Truong Van Khoi |  | Done |  | 2
[UI Mockup Web] User's Hotel Screen | 2 | Truong Van Khoi |  | Done |  | 2
[UI Mockup Web] User's Blog Screen | 1 | Truong Van Khoi |  | Done |  | 1
[UI Mockup Web] User's Contact Screen | 1 | Truong Van Khoi |  | Done |  | 1
[UI Mockup Web] User's Search Screen | 2 | Truong Van Khoi |  | Done |  | 1
[UI Mockup Web] User's Search Hotel Model | 2 | Truong Van Khoi |  | Done |  | 1
[UI Mockup Web] User's Search Tour Model | 3 | Truong Van Khoi |  | Done |  | 3
[UI Mockup Web] User's Update User | 2 | Truong Van Khoi |  | Done |  | 2
[UI Mockup Web] User's Tour Model | 3 | Truong Van Khoi |  | Done |  | 3
[UI Mockup Web] User's Register Model | 3 | Truong Van Khoi |  | Done |  | 1
[UI Mockup Web] User's Hotel Model | 3 | Truong Van Khoi |  | Done |  | 3
[UI Mockup Web] User's Home Controller | 3 | Truong Van Khoi |  | Done |  | 1
[UI Mockup Web] User's Create Store Procedure in SQL | 2 | Truong Van Khoi |  | Done |  | 3
Total | 34 |  | 69.39% |  | Done task: | 85.29%